## Sheet1
Customer Billing System
Project Leader- Shubham Patil
Timeline For Project
TASK | ASSIGNED TO | PROGRESS | START | END | Timeline and hours
Phase 1 Title
Requirements | Shubham Patil | 100% | 2022-03-15 | 2022-03-18 |  | 5hr
Architecture | Shubham Patil | 100% | 2022-03-18 | 2022-03-20 |  |  | 6hr
Implementation | Shubham Patil | 100% | 2022-03-21 | 2022-03-25 |  |  |  | 8hr
TestPlanAndoutput | Shubham Patil | 100% | 2022-03-26 | 2022-03-27 |  | 4hr
Report, Images | Shubham Patil | 100% | 2022-03-28 | 2022-03-30 | 2hr